Her Majesty’s Inspectorate of Probation (HMIP) Report Published 15th December 2014 – Transforming Rehabilitation, Early Implementation.

A Parliamentary briefing from Napo, the Trade Union and Professional Association for Probation and Family Court Staff

Today’s report published by HMIP raises a number of significant concerns in relation to the implementation of the Governments reforms of the Probation Service. The contracts for the new probation providers are due to be signed on Thursday 18th December 2014 with a view to the contracts being mobilised in February 2015. However, the report contains 68 recommendations which Napo believes should be acted on, resolved and evidenced to be working prior to any contracts being signed by preferred bidders. In his foreword the Chief Inspector says:

“there remains significant challenges in getting court end processes working as they should”

“lack of staff in some areas of the National Probation Service was having a detrimental impact on the delivery of some services being provided.”

The interface between the National Probation Service and the Community Rehabilitation Companies will continue to cause challenges that need to be addressed.”

“IT continues to provide a predictable challenge….There is a risk that increased bureaucracy could stifle future innovation, so the issues raised by staff about IT requires serious attention.”

“The speed of the implementation has in itself caused operational problems that could have been avoided.”

“There is no doubt at all that there remains much more to do.”

The 68 recommendations in the report include:

12. The National Probation Service (NPS) senior managers should make arrangements for responses from Police domestic abuse units and children’s services to be received on the day in cases where an oral report (for the Court) is prepared.

A much greater number of offenders are being sentenced at Court using oral reports. Whilst this allows for speedy justice, without the necessary assessments being carried out with the above services there is a real risk that child protection issues and domestic violence concerns will go missed. Cases could be inappropriately allocated to the wrong organisation or grade of staff and not be properly managed during their sentence leading to a direct risk to the public.

15. National Probation Service managers should ensure that Offender Assessment System Risk of Serious Harm screenings are completed routinely at the report stage before any assignment of the case.

This is vital to highlighting risk of harm issues and failing to do so could lead to cases being allocated to the wrong organisation and risk issues to victims and children being missed.

18. The National Offender Management Service should ensure that a re-evaluation of the resources available to the National Probation Service to complete the new workload requirements should be urgently undertaken, particularly in relation to work in courts. (para 1.3, 1.9, 1.21, 2.11)

Napo has continually raised its concerns regarding staff shortages and that the workload in the National Probation Service is much higher than originally planned for. A lack of resources has led to high workloads, increased sickness and low staff morale.

41. Home visits should be completed by all Community Rehabilitation Company offender managers in cases where there are concerns about domestic abuse and/or safeguarding children. (para 3.23)

It is of concern that home visits had only taken place for 5 out of 35 cases where there were domestic violence or safeguarding issues. The report does not offer an explanation of for this but Napo’s own intelligence suggests that it is as a result of staff shortages and cases being allocated to inexperienced or unqualified staff.

46. Community Rehabilitation Company chief executives should clarify what type of case is appropriate for probation service officers (less qualified staff) to manage. (para 3.30)

There is increasing evidence from our members that probation service officers (PSO’s) are being allocated complex cases that are above and beyond their training and experience. This will lead to the de-professionalising of the service and cases not being safely managed in the community. This recommendation should be in place prior to any contracts being signed.

52. Community Rehabilitation Company chief executives should ensure full implementation of workload monitoring (para 3.29)

As yet there is no agreed workload management tool for either the NPS or the CRC’s.

56. National Probation Service (NPS) managers should ensure that home visits are taking place where appropriate, when the offender is classified high risk of serious harm, where there is a history of sexual offences or domestic abuse or where there are child protection concerns. (para 4.8)

This is not happening in the majority of cases looked at by the Inspectorate. Napo believes this is due to high workloads as a result of staff shortages and increased bureaucracy that has been introduced to the system. Home visits are vital for risk management and effective multi agency working.

58. The NPS should undertake a full review of the numbers and proportion of probation officers, probation service officers and administrative staff it employs so that all tasks can be completed efficiently. (para 4.16)

There is a clear disparity across the country of the role of PSO’s in the NPS. The inspectorate had reservations about the types of cases some PSO’s were being expected to manage in some areas. It was also identified that there may be too many PSO’s in the NPS and the original assignment process had not been effective.

59. The National Offender Management Service should review the roles and responsibilities of PSO’s and the training required to support them in their work and professional development.

Napo would urge all parliamentarians to read the report in full. It is of great concern that such a large number of issues remain unresolved yet the Justice Secretary still intends to sign 10 year contracts this week. We believe he should be held to account for this decision, provide evidence to the House and to the preferred bidders on why he believes it is safe to proceed to contract singing and how he intends to implement the recommendations before February 2015.

As a result of Napo’s legal challenge which concluded last week, further evidence from the Ministry of Justice was provided to us that causes further concern. However, due a confidentiality order issued by the Court, Napo is unable to share this information. It is in our view, a concern that the Justice Secretary continues to hide evidence that we believe should be in the public domain. It should be made available to preferred bidders prior to contracts being signed and should also be made available to the House so that he can be held to account for his actions.

Questions you may wish to ask:

- Can the Secretary of State assure the House that all of the key recommendations in the HMIP report have either been implanted or at least will be prior to contracts being signed on 18th December?

- If not what assurances can he give the House that contracts will be ready to be mobilised in February 2015?

- Will the Secretary of State provide the evidence that Napo reference to the House for full parliamentary scrutiny?

- Given the coalition said that they would not proceed to the signing of contracts if the HMIP raised any concerns, can the Justice Secretary now explain why he is proceeding when a significant issues have come to light?

- Why does the Justice Secretary not postpone the signing of contracts until all of these recommendations are in place?

Below is link to the full report:

http://www.justiceinspectorates.gov.uk/hmiprobation/wp-content/uploads/sites/5/2014/12/Transforming_Rehabilitation-Early_Implementation1.pdf